## Sponsor Inputs
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
As a < type of user >, I want < some goal > so that < some reason >
1 | Create Account | As a customer, I want to create account so that I can save my past orders | Medium |  | 3
|  | As a customer, I want to create account so that I personalize my recommendations | Low |  | 5
|  | As a customer, I want to create account so that I can Add my Info | High |  | 1
2 | View Restaurants | As a customer, I want view restaurants so that I can sort by distance from me | Medium |  | 4
|  | As a customer, I want view restaurants so that I can see ther info and ratings | High |  | 1
|  | As a restaurant owner, I want view restaurants so that I can see compitiors in area | Low |  | 5
|  | As a customer, I want view restaurants so that I can see all availabe resturants that dilver to me | High |  | 1
3 | Search Restaurants | As a customer, I want search restaurants so that I can see all the available catigoreis of food | High |  | 1
|  | As a customer, I want search restaurants so that I can find a particular resturant | High |  | 2
4 | View Menu | As a customer, I want view menu so that I can see description and price of every Item | High |  | 2
|  | As a customer, I want view menu so that I can order particular meal | High |  | 1
|  | As a customer, I want view menu so that I can add extra ingredient to the meal | Medium |  | 3
5 | Add to Cart | As a customer, I want add items to cart so that I can see the total price | High |  | 1
|  | As a customer, I want add items to cart so that I can apply promocode | Low |  | 4
6 | Purchase | As a customer, I want purchase items so that I can pay with different methods | Medium |  | 3
7 | Restaurant views order | As a restaurant owner, I want view orders so that I can set there status | High |  | 2
|  | As a restaurant owner, I want view orders so that I can set the preparation time | Medium |  | 3
|  | As a restaurant owner, I want view orders so that I can analiyse how fequent particular meals are ordered | Low |  | 5
|  | As a restaurant owner, I want view orders so that I can make discounts for least selling items | Low |  | 4
8 | Restaurant marks order as delivered | As a restaurant owner, I want mark orders as delivered so that I can calculate my profit | Medium |  | 3